## Process Flow
PQRS Process Flow
Project Life Cycle - Agile Approach
| Pre Sales | Pre Sale Meeting
Project Proposal Preparation
Cost Estimation
| Project Initiation | Kick Off Meeting | Discussion on project | Identify business needs | Understand System Flow
Define Project Vision
|  | Project Requirement Brief | Detail the req. brief from client | Ask additional questions
| Project Planning | Requirement Gathering Meeting
Functional Requirement Brief
Design Requirement Brief
Analysis based on requirement
|  | Requirement Socping | Document the project scope | Share with client
Scope Approval from Client
Requirement Documentation
|  | Project Schedule Planning | Schedule project activities | Send for Approval
Project WBS Preparation
| Project Design | Define Architecture
Create Site Map/Wireframes
Execute Design Standards
Create Design Templates
Design Approval by Client
Finalize Design
Home Page Design
Inner Page Design
Content Design
Design Reviewed as per Standards
HTML Design to Developer
Database Design
| Development | Create Modules
Execute Development Standards
Module Wise Coding
Unit Test Module as per Standards
| Testing | Test Script Preparation | Design Testing | Testing as per checklist | Responsive Layout Testing | Different Browser Testing
Creating Test Scenario
|  | First Round Testing | Development Testing | Testing as per checklist | Functionality Testing
Executing Design Testing Checklist
Executing Development Testing Checklist
Bug Report Preparation
Resolve Bugs
Second Round Testing
| UAT | UAT Testing
Bug Report Preparation (If Any)
Resolve Bugs (If Any)
| Implementation | Delivery
Deployment on Server
Data Configuration
User Training
Project Fundamentals
| Project Approach | Agile Methodology
| Project Types | Web base application
Mobile Application
| App Technology | Dot Net/ PHP/ Drupal
| App Frameworks | Dot Net Framework 4.0
| DB Technology | MS SQL 2008 R2
| Architecture | 3 - Tier Architecture

## Project Scope
| Homoeopathy System Scope | [12 empty] | UAT Deployment |  |  | Live Deployment
ID | Description | Type | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Exp End Date | Closed Date | Remarks | Deployment Release | Release Date | Release Remarks | Deployment Release | Release Date | Release Remarks
1 | Project kick off meeting |  | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
2 | Analysis & requirement gathering |  | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
3 | Wireframe diagram preparation |  | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
4 | Database designing |  | Technople | Change | Dev | Priority 1 | Done | TBD |  | 2014-10-12
5 | Login
6 | Login page design | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
7 | Login page development | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
8 | Creation of different roles (Admin/others) | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
9 | Home
10 | Creating Menu & its sub menus | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
11 | Add Patient Complaints
12 | Search a patient | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
13 | Dynamically display field labels and their respective selection data | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
14 | Add new complaint against the search patient | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
15 | Display available medicines | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
16 | Medicine selection as per complaint | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
17 | On selecting medicine, it should deduct from inventory | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
18 | Display patients visits history | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
19 | Edit/delete patient complaints | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
20 | Validation to select option as per the plan type | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
21 | Validations for all fields | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
22 | Generate Invoice
23 | Search patient | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
24 | Add patient wise invoice details | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
25 | Add payment details | In Scope | Technople | Change | Dev | Priority 1 | In Progress | TBD
26 | On saving update in table the latest balance | In Scope | Technople | Change | Dev | Priority 1 | In Progress | TBD
27 | Invoice layout designing | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
28 | Print invoice | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
29 | Export invoice | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
30 | Mail invoice to patient | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
31 | Validations for all fields | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
32 | Inventory Transaction
33 | Add inventory transaction | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
34 | Reflect transaction entry in DB as per doctor/clinic | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
35 | View current inventory status | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
36 | Validations for all fields | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
37 | Account Entries
38 | Adding new acconting entry (credit/debit) | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
39 | Capturing payment details for credit entries | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
40 | Viewing pending payment details | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
41 | Edit/delete existing accounting entries | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
42 | Program
43 | Attribute Master
44 | Screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
45 | Adding new attribute entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
46 | View/Edit/Delete existing entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
47 | Attribute Parameters Entry
48 | Add new data from through screen and saving in DB | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2014
49 | Viewing existing data | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2015
50 | Edit/delete existing data | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2016
51 | Program Mapping
52 | Screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
53 | Adding new entry by mapping/linking the data through drop down selection | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
54 | Add medicine as per complaint | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
55 | Viewing already mapped entries | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
56 | Edit/delete already mapped entries | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
57 | Account Settings (Admin)
58 | Create Account | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
59 | Edit/Delete user account | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
60 | Create Role | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
61 | Edit/delete role | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
62 | Role mapping to user accounts | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
63 | Validations for all fields | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
64 | User Account
65 | Change password | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
66 | Form validation | In Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
67 | Subscription Plans
68 | Create plan | Out Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
69 | Edit/delete plan | Out Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
70 | Validations for all fields | Out Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD
71 | Master
72 | Patient Master
73 | Patient master screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
74 | Add new patient entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
75 | Search/view existing patients | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
76 | Edit/delete existing patients | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
79 | Upload provision for patient display pic | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
80 | Add reference from doctor field | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
81 | Add field related to | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
82 | Display relation tree | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
83 | Validations for all fields | In Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
84 | Inventory Master
85 | Inventory master screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
86 | Add new inventory entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
87 | Search/view existing inventory details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
88 | Edit/delete existing inventory details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
89 | Add sundry items | Out Scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-12
90 | Doctor Master
91 | Doctor master screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
92 | Add new Doctor entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
93 | Search/view existing doctor details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
94 | Edit/delete existing doctor details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
95 | Display refered to details | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
96 | Display patient details in refered to to (medicine details) | Out Scope | Technople | Change | Dev | Priority 1 | TBD | TBD
97 | Clinic Master
98 | Clinic master screen designing | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
99 | Add new clinic entry | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
100 | Search/view existing clinic details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
101 | Edit/delete existing clinic details | In scope | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
102 | Reports
103 | Patient Report | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
104 | Account Report | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
105 | Inventory Report | In scope | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
106 | Testing
107 | First Round Testing |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
108 | Resolve Bugs |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
109 | Second Round Testing |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
110 | UAT Testing
111 | Resolve Bugs (If Any) |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
Go Live

## Project WBS
| WBS | [18 empty] | UAT Deployment |  |  | Live Deployment
ID | Description | Resource | Type | Design Days | Dev Days | Estimated Days | Actual Days | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Start Date | Exp End Date | Closed Date | Remarks | Deployment Release | Release Date | Release Remarks | Deployment Release | Release Date | Release Remarks
1 | Project kick off meeting | Aditya |  |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
2 | Analysis & requirement gathering | Aditya |  |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
3 | Wireframe diagram preparation | Aditya |  |  |  | 1 | 1 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
4 | Database designing | Minakshi |  |  |  | 2 | 2 | Technople | Change | Dev | Priority 1 | Done | TBD |  | 2014-10-12
5 | Login
6 | Login page design | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
7 | Login page development | Minakshi | In scope |  |  | 0.5 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
8 | Creation of different roles (Admin/others) | Minakshi | In scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
9 | Home
10 | Creating Menu & its sub menus | Minakshi | In scope |  |  | 0.25 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
11 | Add Patient Complaints
12 | Search a patient | Minakshi | In Scope |  |  | 0.125 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
13 | Dynamically display field labels and their respective selection data | Minakshi | In Scope |  |  | 1 | 2 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
14 | Add new complaint against the search patient | Minakshi | In Scope |  |  | 0.5 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
15 | Display available medicines | Minakshi | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
16 | Medicine selection as per complaint | Minakshi | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
17 | On selecting medicine, it should deduct from inventory | Minakshi | In Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
18 | Display patients visits history | Minakshi | In Scope |  |  | 0.5 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
19 | Edit/delete patient complaints | Minakshi | In Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
20 | Validation to select option as per the plan type | Minakshi | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
21 | Validations for all fields | Minakshi | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
22 | Generate Invoice
23 | Search patient | Rupesh | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
24 | Add patient wise invoice details | Rupesh | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
25 | Add payment details | Rupesh | In Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  |  | 2015-02-16
26 | On saving update in table the latest balance | Rupesh | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  |  | 2015-02-16
27 | Invoice layout designing | Rupesh | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
28 | Print invoice | Rupesh | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
29 | Export invoice | Rupesh | In Scope |  |  | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
30 | Mail invoice to patient | Rupesh | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
31 | Validations for all fields | Rupesh | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
32 | Inventory Transaction | [17 empty] | Screen details yet to be confirmed from client
33 | Add inventory transaction |  | In Scope |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
34 | Reflect transaction entry in DB as per doctor/clinic |  | In Scope |  |  | 0.75 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
35 | View current inventory status |  | In Scope |  |  | 0.75 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
36 | Validations for all fields |  | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
37 | Account Entries | [17 empty] | Screen details yet to be confirmed from client
38 | Adding new acconting entry (credit/debit) | Arvind | In scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
39 | Capturing payment details for credit entries | Arvind | In scope |  |  | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
40 | Viewing pending payment details | Arvind | In scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
41 | Edit/delete existing accounting entries | Arvind | In scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
42 | Program
43 | Attribute Master
44 | Screen designing | Arvind | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
45 | Adding new attribute entry | Arvind | In scope |  |  | 0.5 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
46 | View/Edit/Delete existing entry | Arvind | In scope |  |  | 0.25 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
47 | Attribute Parameters Entry
48 | Add new data from through screen and saving in DB | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2014
49 | Viewing existing data | Minakshi | In scope |  |  | 0.125 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2015
50 | Edit/delete existing data | Minakshi | In scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2016
51 | Program Mapping
52 | Screen designing | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
53 | Adding new entry by mapping/linking the data through drop down selection | Minakshi | In scope |  |  | 0.5 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
54 | Add medicine as per complaint | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
55 | Viewing already mapped entries | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
56 | Edit/delete already mapped entries | Minakshi | In scope |  |  | 0.75 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
57 | Account Settings (Admin)
58 | Create Account | Rupesh | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
59 | Edit/Delete user account | Rupesh | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
60 | Create Role | Rupesh | In Scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
61 | Edit/delete role | Rupesh | In Scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
62 | Role mapping to user accounts | Rupesh | In Scope |  |  | 1 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
63 | Validations for all fields | Rupesh | In Scope |  |  | 0.5 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
64
65 | User Account
66 | Change password |  | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
67 | Form validation |  | In Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
68
69 | Subscription Plans
70 | Create plan |  | Out Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
71 | Edit/delete plan |  | Out Scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
72 | Validations for all fields |  | Out Scope |  |  | 0.5 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
73 | Master
74 | Patient Master
75 | Patient master screen designing | Minakshi | In scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
76 | Add new patient entry | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
77 | Search/view existing patients | Minakshi | In scope |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
78 | Edit/delete existing patients | Minakshi | In scope |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
79 | Upload provision for patient display pic |  | Out Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
80 | Add reference from doctor field |  | Out Scope |  |  | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
81 | Add field related to |  | Out Scope |  |  | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
82 | Display relation tree |  | Out Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
83 | Validations for all fields |  | In Scope |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
84 | Inventory Master
85 | Inventory master screen designing | Rupesh | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
86 | Add new inventory entry | Rupesh | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
87 | Search/view existing inventory details | Rupesh | In scope |  |  | 0.125 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
88 | Edit/delete existing inventory details | Rupesh | In scope |  |  | 0.125 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
89 | Add sundry items | Rupesh | Out Scope |  |  | 0.5 | 1.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-12
90 | Doctor Master
91 | Doctor master screen designing | Minakshi | In scope |  |  | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
92 | Add new Doctor entry | Minakshi | In scope |  |  | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
93 | Search/view existing doctor details | Minakshi | In scope |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
94 | Edit/delete existing doctor details | Minakshi | In scope |  |  | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
95 | Display refered to details |  | Out Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
96 | Display patient details in refered to to (medicine details) |  | Out Scope |  |  | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
97 | Clinic Master
98 | Clinic master screen designing | Arvind | In scope |  |  | 0.25 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
99 | Add new clinic entry | Arvind | In scope |  |  | 0.25 | 2 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
100 | Search/view existing clinic details | Arvind | In scope |  |  | 0.125 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
101 | Edit/delete existing clinic details | Arvind | In scope |  |  | 0.125 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
102 | Reports | [17 empty] | Screen details yet to be confirmed from client
103 | Patient Report | Minakshi | In scope |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
104 | Account Report | Minakshi | In scope |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
105 | Inventory Report | Minakshi | In scope |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
106 | New CR Changes - As per Meeting 12 Feb 2015
107 | Program Mapping - Multiple |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
108 | Screen designing |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
109 | Display parameters with checkbox selection |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
110 | Adding new entry by mapping/linking the data through drop down selection |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
111 | Add medicine as per multiple chain selected |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
112 | Viewing already mapped multiple entries |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
113 | Edit/delete already mapped entries |  | In scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
114 | Add Complaint - Multiple Illness |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
115 | Search a patient |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
116 | Dynamically display field labels and their respective selection data in the defined sequence |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
117 | Display selection values with checkbox option |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
118 | Add multiple complaint against the search patient |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
119 | Display available medicines |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
120 | On displaying medicine, it should deduct from inventory |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
121 | Display patients visits history |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
122 | Edit/delete patient complaints |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
123 | Validation to select option as per the plan type |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
124 | Validations for all fields |  | In Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
125 | Add Complaint - Non User |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
126 | Form designing |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
127 | Dynamically display field labels and their respective selection data in the defined sequence |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
128 | Display selection values |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
129 | Allow non logged in user to add illness complaint |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
130 | Provide selection for user as- Request for medicine Advice for medicine |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
131 | On displaying medicine, it should deduct from inventory |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
132 | Submit complaints in form of email to the admin |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
133 | Thank & get back to you shortly acknowledgement message |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
134 | Form validation |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
135 | Reply Complaint - Anonymous User |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
136 | Receive non user complaint in email |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
137 | Bifurcate complaints as per type- Request for medicine Advice for medicine |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
138 | Multiple Medicine Fields while creating mapping |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
139 | Provision for admin to add more than one medicine fields at attribute master page |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
140 | Provision for admin to add mutiple parameters in medicine attribute at attribute parameters page |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
141 | Admin on creating and saving a mapping chain he will select values (parameters) from available medicine attributes |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
142 | The selected value (parameter) shall be saved for that particular program mapping chain |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
143 | Mapping user Subscription plan with medicine |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
144 | At the time of creating subscription plan, admin will map medicine attribute to each subscription plan |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
145 | when a particular plan user logs in to system he/she will be able to see the mapped medicine attribute |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
146 | Promotional Packages |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
147 | A new page of program mapping with following fields: Section Illness |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
148 | Provision for admin to select date at which the above mapping fields shall be available for users to raise a complaint |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
149 | As per the selected date, a custom add complaint page to be displayed for non logged in users to raise a complaint |  | Out Scope |  |  | 0 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
150 | Testing
151 | First Round Testing |  |  |  |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
152 | Resolve Bugs |  |  |  |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
153 | Second Round Testing |  |  |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
154 | UAT Testing
155 | Resolve Bugs (If Any) |  |  |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
[6 empty] | 37.75 | 30.5

## Pending Development Scope (hidden)
| Homoeopathy System Scope | [15 empty] | Deployment Status
ID | Description | Resource | Type | Estimated Days | Actual Days | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Exp End Date | Closed Date | Remarks | Deployment Release | Release Date | Release Remarks
Add Patient Complaints
| Search a patient | Minakshi | In Scope | 0.125 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
| Dynamically display field labels and their respective selection data | Minakshi | In Scope | 1 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD
| Add new complaint against the search patient | Minakshi | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD
| Display available medicines | Minakshi | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Medicine selection as per complaint | Minakshi | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| On selecting medicine, it should deduct from inventory | Minakshi | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Display patients visits history | Minakshi | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Edit/delete patient complaints | Minakshi | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validation to select option as per the plan type | Minakshi | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields | Minakshi | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Generate Invoice
| Search patient | Rupesh | In Scope | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
| Add patient wise invoice details | Rupesh | In Scope | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD
| Add payment details | Rupesh | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD
| On saving update in table the latest balance | Rupesh | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Invoice layout designing | Rupesh | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Print invoice | Rupesh | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Export invoice | Rupesh | In Scope | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Mail invoice to patient | Rupesh | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields | Rupesh | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Inventory Transaction
| Add inventory transaction |  | In Scope | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Reflect transaction entry in DB as per doctor/clinic |  | In Scope | 0.75 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| View current inventory status |  | In Scope | 0.75 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Account Settings (Admin)
| Create Account |  | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Edit/Delete user account |  | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Create Role | Rupesh | In Scope | 0.25 | 0.375 | Technople | Change | Dev | Priority 1 | TBD | TBD |  |  |  | 2015-01-13
| Edit/delete role | Rupesh | In Scope | 0.25 | 0.375 | Technople | Change | Dev | Priority 1 | TBD | TBD |  |  |  | 2015-01-13
| Role mapping to user accounts |  | In Scope | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
User Account
| Change password |  | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Form validation |  | In Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Subscription Plans
| Create plan |  | Out Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Edit/delete plan |  | Out Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | Out Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Patient Master
| Upload provision for patient display pic |  | Out Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Add reference from doctor field |  | Out Scope | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Add field related to |  | Out Scope | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Display relation tree |  | Out Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | In Scope | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
Inventory Master
| Add sundry items | Rupesh | Out Scope | 0.5 | 1.75 | Technople | Change | Dev | Priority 1 | TBD | TBD |  |  |  | 2015-01-12
Doctor Master
| Display refered to details |  | Out Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Display patient details in refered to to (medicine details) |  | Out Scope | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Account Entries |  | In Scope |  |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  |  |  |  | Screen yet to be finalised
| Reports |  | In Scope |  |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  |  |  |  | Screen yet to be finalised
Testing
| First Round Testing |  |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Resolve Bugs |  |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Second Round Testing |  |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
UAT Testing
| Resolve Bugs (If Any) |  |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD
| Go Live | Total Days |  | 18.375 | 3.25

## Homoeopathy System_Old (hidden)
| Homoeopathy System Status | [14 empty] | Deployment Status
ID | Description | Resource | Estimated Days | Actual Days | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Exp End Date | Closed Date | Remarks | Deployment Release | Release Date | Release Remarks
CH_01 | Project kick off meeting | Aditya | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
CH_02 | Analysis & requirement gathering | Aditya | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
CH_03 | Wireframe diagram preparation | Aditya | 1 | 1 | Technople | Change | Dev | Priority 1 | Done | NA |  | 2014-10-12
CH_04 | Database designing | Minakshi | 2 | 2 | Technople | Change | Dev | Priority 1 | Done | TBD |  | 2014-10-12
CH_05 | Login
CH_06 | Login page design | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_07 | Login page development | Minakshi | 0.5 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_08 | Creation of different roles (Admin/others) | Minakshi | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_09 | Home
CH_10 | Creating Menu & its sub menus | Minakshi | 0.25 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_11 | Add Patient Complaints
CH_12 | Search a patient | Minakshi | 0.125 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
CH_13 | Add new complaint against the search patient | Minakshi | 0.5 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2014-12-22
CH_14 | Display medicine as per complaint | Minakshi | 0.125 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2014-12-22
CH_15 | Display patients complaint history | Minakshi | 0.25 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2014-12-23
CH_16 | Edit/delete patient complaints | Minakshi | 0.25 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2014-12-23
CH_17 | Generate Invoice
CH_18 | Generate patient wise invoice | Rupesh | 0.25 |  | Technople | Change | Dev | Priority 1 | In Progress | TBD |  | 2014-12-22
CH_19 | Invoice structure designing | Rupesh | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-22
CH_20 | Calculate & display invoice amount as per medicines | Rupesh | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
CH_21 | Save/Print/Mail invoice | Rupesh | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
CH_22 | Account Entries
CH_23 | Adding new acconting entry (credit/debit) | Arvind | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
CH_24 | Capturing payment details for credit entries | Arvind | 0.125 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
CH_25 | Viewing pending payment details | Arvind | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
CH_26 | Edit/delete existing accounting entries | Arvind | 0.25 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
CH_27 | Program
CH_28 | Attribute Master
CH_29 | Screen designing | Arvind | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_30 | Adding new attribute entry | Arvind | 0.5 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_31 | View/Edit/Delete existing entry | Arvind | 0.25 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_32 | Attribute Parameters Entry
CH_33 | Add new data from through screen and saving in DB | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2014
CH_34 | Viewing existing data | Minakshi | 0.125 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2015
CH_35 | Edit/delete existing data | Minakshi | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2016
CH_36 | Program Mapping
CH_37 | Screen designing | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
CH_38 | Adding new entry by mapping/linking the data through drop down selection | Minakshi | 0.5 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
CH_39 | Add medicine as per complaint | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
CH_40 | Viewing already mapped entries | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
CH_41 | Edit/delete already mapped entries | Minakshi | 0.75 | 0.75 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
CH_42 | Master
CH_43 | Patient Master
CH_44 | Patient master screen designing | Minakshi | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_45 | Add new patient entry | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_46 | Search/view existing patients | Minakshi | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_47 | Edit/delete existing patients | Minakshi | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_48 | Inventory Master
CH_49 | Inventory master screen designing | Rupesh | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_50 | Add new inventory entry | Rupesh | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_51 | Search/view existing inventory details | Rupesh | 0.125 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_52 | Edit/delete existing inventory details | Rupesh | 0.125 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_53 | Doctor Master
CH_54 | Doctor master screen designing | Minakshi | 0.25 | 0.5 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_55 | Add new Doctor entry | Minakshi | 0.25 | 0.25 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_56 | Search/view existing doctor details | Minakshi | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_57 | Edit/delete existing doctor details | Minakshi | 0.125 | 0.125 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_58 | Clinic Master
CH_59 | Clinic master screen designing | Arvind | 0.25 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_60 | Add new clinic entry | Arvind | 0.25 | 2 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_61 | Search/view existing clinic details | Arvind | 0.125 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_62 | Edit/delete existing clinic details | Arvind | 0.125 | 1 | Technople | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
CH_63 | Reports
CH_64 | Patient Report | Minakshi | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
CH_65 | Account Report | Minakshi | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_66 | Inventory Report | Minakshi | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_67 | Testing
CH_68 | First Round Testing |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_69 | Resolve Bugs |  | 2 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_70 | Second Round Testing |  | 0.5 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
CH_71 | UAT Testing
CH_72 | Resolve Bugs (If Any) |  | 1 |  | Technople | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
| Go Live | Total Days | 23.5 | 20.75

## WBS Plan
WBS
|  | Estimated Hours |  |  | Actual Hours |  |  |  |  | Development Tracking | [10 empty] | UAT Deployment |  |  | Live Deployment
Project Phase | Activity | Design | Dev | Total | Design | Dev | Total | Resource | Scope Type | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Start Date | Exp End Date | Closed Date | Remarks | Deployment Release | Release Date | Release Remarks | Deployment Release | Release Date | Release Remarks
Development | Login |  |  | 0 |  |  | 0
| Login page design |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Login page development |  | 4 | 4 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Creation of different roles (Admin/others) |  | 2 | 2 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
| Home |  |  | 0 |  |  | 0
| Creating Menu & its sub menus |  | 2 | 2 |  | 6 | 6 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add Patient Complaints |  |  | 0 |  |  | 0
| Search a patient |  | 1 | 1 |  | 2 | 2 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Dynamically display field labels and their respective selection data |  | 8 | 8 |  | 16 | 16 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Add new complaint against the search patient |  | 4 | 4 |  | 4 | 4 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Display available medicines |  | 2 | 2 |  | 2 | 2 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Medicine selection as per complaint |  | 2 | 2 |  | 2 | 2 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| On selecting medicine, it should deduct from inventory |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Display patients visits history |  | 4 | 4 |  | 4 | 4 | Minakshi | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Edit/delete patient complaints |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Validation to select option as per the plan type |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Generate Invoice |  |  | 0 |  |  | 0
| Search patient |  | 2 | 2 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Add patient wise invoice details |  | 2 | 2 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Add payment details |  | 2 | 2 |  | 8 | 8 | Rupesh | In Scope | Change | Dev | Priority 1 | In Progress | TBD |  |  | 2015-02-16
| On saving update in table the latest balance |  | 4 | 4 |  | 8 | 8 | Rupesh | In Scope | Change | Dev | Priority 1 | In Progress | TBD |  |  | 2015-02-16
| Invoice layout designing |  | 4 | 4 |  |  | 0 | Rupesh | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Print invoice |  | 4 | 4 |  |  | 0 | Rupesh | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Export invoice |  | 1 | 1 |  |  | 0 | Rupesh | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Mail invoice to patient |  | 4 | 4 |  |  | 0 | Rupesh | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | 4 | 4 |  |  | 0 | Rupesh | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Inventory Transaction |  |  | 0 |  |  | 0 | [12 empty] | Screen details yet to be confirmed from client
| Add inventory transaction |  | 8 | 8 |  |  | 0 |  | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Reflect transaction entry in DB as per doctor/clinic |  | 6 | 6 |  |  | 0 |  | In Scope | Change | Dev | Priority 1 | TBD | TBD
| View current inventory status |  | 6 | 6 |  |  | 0 |  | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | 4 | 4 |  |  | 0 |  | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Account Entries |  |  | 0 |  |  | 0 | [12 empty] | Screen details yet to be confirmed from client
| Adding new acconting entry (credit/debit) |  | 4 | 4 |  |  | 0 | Arvind | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
| Capturing payment details for credit entries |  | 1 | 1 |  |  | 0 | Arvind | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-23
| Viewing pending payment details |  | 2 | 2 |  |  | 0 | Arvind | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
| Edit/delete existing accounting entries |  | 2 | 2 |  |  | 0 | Arvind | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
| Program |  |  | 0 |  |  | 0
| Attribute Master |  |  | 0 |  |  | 0
| Screen designing |  | 2 | 2 |  | 4 | 4 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Adding new attribute entry |  | 4 | 4 |  | 6 | 6 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| View/Edit/Delete existing entry |  | 2 | 2 |  | 8 | 8 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Attribute Parameters Entry |  |  | 0 |  |  | 0
| Add new data from through screen and saving in DB |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2014
| Viewing existing data |  | 1 | 1 |  | 2 | 2 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2015
| Edit/delete existing data |  | 2 | 2 |  | 2 | 2 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 18/12/2016
| Program Mapping |  |  | 0 |  |  | 0
| Screen designing |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
| Adding new entry by mapping/linking the data through drop down selection |  | 4 | 4 |  | 6 | 6 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
| Add medicine as per complaint |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-22
| Viewing already mapped entries |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
| Edit/delete already mapped entries |  | 6 | 6 |  | 6 | 6 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-12-23
| Account Settings (Admin) |  |  | 0 |  |  | 0
| Create Account |  | 2 | 2 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Edit/Delete user account |  | 2 | 2 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Create Role |  | 2 | 2 |  | 4 | 4 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
| Edit/delete role |  | 2 | 2 |  | 4 | 4 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-13
| Role mapping to user accounts |  | 8 | 8 |  | 8 | 8 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Validations for all fields |  | 4 | 4 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| User Account |  |  | 0 |  |  | 0
| Change password |  | 2 | 2 |  | 4 | 4 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Form validation |  | 2 | 2 |  | 2 | 2 | Rupesh | In Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Subscription Plans |  |  | 0 |  |  | 0
| Create plan |  | 2 | 2 |  | 4 | 4 | Rupesh | Out Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Edit/delete plan |  | 2 | 2 |  | 4 | 4 | Rupesh | Out Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Validations for all fields |  | 4 | 4 |  | 4 | 4 | Rupesh | Out Scope | Change | Dev | Priority 1 | Dev Done | TBD
| Master |  |  | 0 |  |  | 0
| Patient Master |  |  | 0 |  |  | 0
| Patient master screen designing |  | 2 | 2 |  | 2 | 2 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add new patient entry |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Search/view existing patients |  | 1 | 1 |  | 1 | 1 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Edit/delete existing patients |  | 1 | 1 |  | 1 | 1 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Upload provision for patient display pic |  | 2 | 2 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Add reference from doctor field |  | 1 | 1 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Add field related to |  | 1 | 1 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Display relation tree |  | 4 | 4 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Validations for all fields |  | 4 | 4 |  |  | 0 |  | In Scope | Change | Dev | Priority 1 | TBD | TBD
| Inventory Master |  |  | 0 |  |  | 0
| Inventory master screen designing |  | 2 | 2 |  | 4 | 4 | Rupesh | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add new inventory entry |  | 2 | 2 |  | 4 | 4 | Rupesh | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Search/view existing inventory details |  | 1 | 1 |  | 4 | 4 | Rupesh | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Edit/delete existing inventory details |  | 1 | 1 |  | 4 | 4 | Rupesh | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add sundry items |  | 4 | 4 |  | 4 | 4 | Rupesh | Out Scope | Change | Dev | Priority 1 | Dev Done | TBD |  |  |  | 2015-01-12
| Doctor Master |  |  | 0 |  |  | 0
| Doctor master screen designing |  | 2 | 2 |  | 4 | 4 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add new Doctor entry |  | 2 | 2 |  | 2 | 2 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Search/view existing doctor details |  | 1 | 1 |  | 1 | 1 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Edit/delete existing doctor details |  | 1 | 1 |  | 1 | 1 | Minakshi | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Display refered to details |  | 2 | 2 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Display patient details in refered to to (medicine details) |  | 2 | 2 |  |  | 0 |  | Out Scope | Change | Dev | Priority 1 | TBD | TBD
| Clinic Master |  |  | 0 |  |  | 0
| Clinic master screen designing |  | 2 | 2 |  | 8 | 8 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Add new clinic entry |  | 2 | 2 |  | 16 | 16 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Search/view existing clinic details |  | 1 | 1 |  | 8 | 8 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Edit/delete existing clinic details |  | 1 | 1 |  | 8 | 8 | Arvind | In scope | Change | Dev | Priority 1 | Dev Done | TBD |  | 2014-10-12
| Reports |  |  | 0 |  |  | 0 | [12 empty] | Screen details yet to be confirmed from client
| Patient Report |  | 8 | 8 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-12-24
| Account Report |  | 8 | 8 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
| Inventory Report |  | 8 | 8 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2014-10-12
New CR Changes - As per Meeting 12 Feb 2015
| Program Mapping - Multiple |  |  | 0 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Screen designing |  | 2 | 2 |  | 5 | 5 | Minakshi | In scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Display parameters with checkbox selection |  | 4 | 4 |  | 12 | 12 | Minakshi | In scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Adding new entry by mapping/linking the data through drop down selection |  | 4 | 4 |  | 12 | 12 | Minakshi | In scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Add medicine as per multiple chain selected |  | 2 | 2 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Viewing already mapped multiple entries |  | 2 | 2 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | In Progress | TBD |  | 2015-02-12 | 2015-02-14
| Edit/delete already mapped entries |  | 6 | 6 |  |  | 0 | Minakshi | In scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Add Complaint - Multiple Illness |  |  | 0 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Search a patient |  | 1 | 1 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Dynamically display field labels and their respective selection data in the defined sequence |  | 8 | 8 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Display selection values with checkbox option |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Add multiple complaint against the search patient |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Display available medicines |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| On displaying medicine, it should deduct from inventory |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Display patients visits history |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Edit/delete patient complaints |  | 2 | 2 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Validation to select option as per the plan type |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Validations for all fields |  | 4 | 4 |  |  | 0 | Minakshi | In Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Add Complaint - Non User |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Form designing |  | 1 | 1 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Dynamically display field labels and their respective selection data in the defined sequence |  | 8 | 8 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Display selection values |  | 4 | 4 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Allow non logged in user to add illness complaint |  | 2 | 2 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Provide selection for user as- Request for medicine Advice for medicine |  | 2 | 2 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| On displaying medicine, it should deduct from inventory |  | 2 | 2 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Submit complaints in form of email to the admin |  | 4 | 4 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Thank & get back to you shortly acknowledgement message |  | 2 | 2 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Form validation |  | 4 | 4 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Reply Complaint - Anonymous User |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Receive non user complaint in email |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Bifurcate complaints as per type- Request for medicine Advice for medicine |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Multiple Medicine Fields while creating mapping |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Provision for admin to add more than one medicine fields at attribute master page |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Provision for admin to add mutiple parameters in medicine attribute at attribute parameters page |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Admin on creating and saving a mapping chain he will select values (parameters) from available medicine attributes |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| The selected value (parameter) shall be saved for that particular program mapping chain |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Mapping user Subscription plan with medicine |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| At the time of creating subscription plan, admin will map medicine attribute to each subscription plan |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| when a particular plan user logs in to system he/she will be able to see the mapped medicine attribute |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Promotional Packages |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| A new page of program mapping with following fields: Section Illness |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| Provision for admin to select date at which the above mapping fields shall be available for users to raise a complaint |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
| As per the selected date, a custom add complaint page to be displayed for non logged in users to raise a complaint |  |  | 0 |  |  | 0 | Minakshi | Out Scope | Change | Dev | Priority 1 | TBD | TBD |  | 2015-02-12
Testing | Execute design checklist |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Execute responsive design checklist |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Execute development checklist |  |  | 0 |  | 20 | 20 | [5 empty] | In Progress | TBD |  |  | 2015-02-09 | 2015-02-09
| Resolve isssues identified in design & dev testing |  |  | 0 |  | 16 | 16 | [5 empty] | In Progress | TBD |  |  | 2015-02-09 | 2015-02-09
| Second round of design testing |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Second round of dev testing |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
UAT | Backup creation of existing UAT version |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Creating UAT deployment patch |  |  | 0 |  | 2 | 2 | [5 empty] | In Progress | TBD |  |  | 2015-02-09 | 2015-02-09
| Deployment of files & DB |  |  | 0 |  | 16 | 16 | [5 empty] | In Progress | TBD |  |  | 2015-02-09 | 2015-02-09
| DB connectivity |  |  | 0 |  | 1 | 1 | [5 empty] | In Progress | TBD |  |  | 2015-02-09 | 2015-02-09
| Client UAT testing |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Resolve issues identified in UAT testing |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
Implementation | Deploy latest patch on server |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| DNS pointing activity |  |  | 0 |  |  | 0 | [5 empty] | TBD | TBD |  |  | 2015-02-09 | 2015-02-09
| Total Hours |  |  | 314 |  |  | 314
| Total Days |  |  | 39.25 |  |  | 39.25

## Design Checklist
Design Checklist
Section | List | Executive | Status | Tested Date
Browser Compatibility | Internet Explorer |  | TBD
| Mozilla Firefox |  | TBD
| Google Chrome |  | TBD
| Safari |  | TBD
| Opera |  | TBD
Resolutions | Mobile portrait (320x480) |  | TBD
| Mobile landscape (480x320) |  | TBD
| Small tablet portrait (600x800) |  | TBD
| Small tablet landscape (800x600) |  | TBD
| Tablet portrait (768x1024) |  | TBD
| Tablet landscape (1024x768) |  | TBD
| Desktop (1366x768) |  | TBD
| Higher Resolution (1920x768) |  | TBD
Alignment | Header |  | TBD
| Banner |  | TBD
| Main Content (side bar) |  | TBD
| Footer |  | TBD
Website Speed | Webpage Response Time: https://developers.google.com/speed/pagespeed/insights/ |  | TBD
Proportions | Webpage Size |  | TBD
| Image size |  | TBD

## Dev Checklist
Development Checklist
Section | List | Executive | Status | Tested Date
Deployment | Old database backup creation (If any) |  | TBD
| Old website backup creation (If any) |  | TBD
| Hosting purchase |  | TBD
| Domain name purchase |  | TBD
| Domain name pointing to hosting |  | TBD
| Upload new files on hosting |  | TBD
| Upload new DB on hosting |  | TBD
| DB connectivity |  | TBD
| Set default page for website |  | TBD
| Clear cache |  | TBD
Website Theme | Bootstrap theme enabled check |  | TBD
Home Page | Favicon |  | TBD
| Tab heading |  | TBD
| On click of logo redirect to home page |  | TBD
| Search bar working for entire website search |  | TBD
Login Screen | Submit & Reset button provided |  | TBD
| Forgot password option provided |  | TBD
| Email functionality on forgot password |  | TBD
| Remember me checkbox provided |  | TBD
| New user signup option (if required) |  | TBD
| User should not be able to paste username/password in respective fields |  | TBD
| Encrypted password saved in DB |  | TBD
Session | If a user logins from one browser, the same time user cannot login from different browser. Either of session to get terminated. |  | TBD
| If a user login is active on a browser and we open admin panel in same browser, that point of time the admin login should not get bypassed |  | TBD
| Session timeout implemented |  | TBD
Footer | Social icons linked to the social media page |  | TBD
| Social media page to open in new tab |  | TBD
Error Handling | Default 404 error page set |  | TBD
All pages | SEO friendly URLs |  | TBD
| All website links working |  | TBD
| Breadcrumbs working |  | TBD
| All images displayed without link break |  | TBD
| Spelling/grammatical checks |  | TBD
| All download options working |  | TBD
| Video getting played in all browsers (if any) |  | TBD
Email | Email getting sent in required scenarios |  | TBD
| Required 'To' & 'Cc' mail address specified in code |  | TBD
| Email subject added as per email type |  | TBD
| Email body well structured |  | TBD
| Email accounts created on hosting server |  | TBD
| Webmail access link provided to client |  | TBD
Contact Us | Inquiry form working |  | TBD
| Inquiry email getting sent |  | TBD
| Users information saved in DB |  | TBD
| Captcha code provided |  | TBD
Forms | Field validation for forms |  | TBD
| First alphabet capital for all field label name |  | TBD
| Submit & Reset button provided while accepting user inputs |  | TBD
| Tool tip text provided for every field |  | TBD
| Confirmation message displayed for any kind of update and delete operation |  | TBD
| Check if the dropdown data is not truncated due to the field size |  | TBD
| Messages to validate mandatory fields |  | TBD
| Character limit set for all fields |  | TBD
| Form to be accessible using keyboard & mouse |  | TBD

## Technople Issue Log
Technople Issue Log
ID | Description | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Exp End Date | Closed Date | Estimated Days | Remarks | Deployment Release | Release Date | Release Remarks
I_01 |  | Technople | Bug | Design | Priority 1 | TBD | TBD

## Client Issue Log
Client Issue Log
ID | Description | Location | Type | Sub Type | Priority | Status | Deployment Status | Raised By | Raised date | Exp End Date | Closed Date | Estimated Days | Remarks | Deployment Release | Release Date | Release Remarks
I_01 |  |  | Bug | Design | Priority 1 | TBD | TBD

## Sheet1
| Level 1 | Level 2 | Level 3
Attributes | Section | Illness | Location
Parameters | Acute Complaints | Headache | Forehead
Right
|  | Pain | Neck
| Old Age Issues | Swelling | Uper Throat
|  | Heat | Chest
Chain Details
Chain 1 | Acute Complaints | Headache | Forehead
Chain 2 | Acute Complaints | Headache | Right
Chain 3 | Acute Complaints | Pain | Neck
Chain 4 | Old Age Issues | Swelling | Uper Throat
Chain 5 | Old Age Issues | Heat | Chest